## Gantt Chart Template
Project Timeline Template
Project Name: Radi Company
| Task Name | Start (Date) | End (Date) | Duration (Days)
| Analisis | 2024-01-22 | 2024-01-24 | 2
| Design/Prototype | 2024-01-24 | 2024-01-27 | 3
| Technical Design | 2024-02-05 | 2024-02-07 | 2
| Architecture Review | 2024-02-07 | 2024-02-07 | 0
| Development | 2024-02-07 | 2024-02-29 | 22
| Deployment | 2024-03-11 | 2024-03-12 | 1
| Testing | 2024-03-13 | 2024-03-25 | 12
| Launch | 2024-03-27 | 2024-03-27 | 0

## How To Use This Template
Introduction
Use this template to help you plan projects! When you update columns B, C, & D in the other tab your gantt chart will automatically update.
Of course, if you need to manage your projects online, in real-time, click the link to the right-----> where you can start your 30-day Free Trial!